## Hoja1
Increment | Phase | % of Effort | Effort (Person x Day) | Subsystem | Increment | % of Effort
Increment 1 | Analysis | 20% | 29.99 | Task Management | 1 | 100
| Design | 20% | 29.99 | Report System | 2 | 28
| Coding | 20% | 29.99 | Fault History and Statistics | 2 | 72
| Unit Tests | 10% | 14.99 | User Management | 3 | 64
| Integration Tests | 20% | 29.99 | Notification and Messaging System | 3 | 36
| Implementation | 10% | 14.99
| Total | 100% | 149.972
Increment 2 | Analysis | 20% | 14.84 | Increment | Subsystems | Incremented FP | Incremented Effort (person x day)
| Design | 20% | 14.84 | Increment 1 | Task Management | 102.3 | 149.972
| Coding | 20% | 14.84 | Increment 2 | Report System, Fault History and Statistics | 50.6 | 74.213
| Unit Tests | 10% | 7.42 | Increment 3 | User Management, Notification and Messaging System | 48.4 | 70.986
| Integration Tests | 20% | 14.84 | Total |  | 201.3 | 295.1058
| Implementation | 10% | 7.42
| Total | 100% | 74.213
Increment 3 | Analysis | 20% | 14.2
| Design | 20% | 14.2
| Coding | 20% | 14.2
| Unit Tests | 10% | 7.1
| Integration Tests | 20% | 14.2
| Implementation | 10% | 7.1
| Total | 100% | 70.986